## ProjectScope
Phase | Item | Category | Task | Owner | Status | Notes
Initiation | Project Onboarding | Standard | Engineer Review of SOW | Lead Engineer
Initiation | Project Onboarding | Standard | Internal Kickoff Call | PM
Initiation | Project Onboarding | Standard | Client Kickoff Call | PM
Initiation | Customer Onboarding | Operator Connect | Enable NWN as Operator Connect provider | Customer
Initiation | Customer Onboarding | DRaaS | NWN Integration through App Auth | Customer
Discovery, Planning, Design | Discovery | Standard | Initial Discovery Meeting with Customer | PM
Discovery, Planning, Design | Discovery | Voice Config | NWN Access | Customer
Discovery, Planning, Design | Discovery | Voice Config | Phone Number Migration - High Level | Lead Engineer
Discovery, Planning, Design | Discovery | Voice Config | Dialing Pattern Requirements | Lead Engineer
Discovery, Planning, Design | Discovery | Voice Config | Routing Requirements (Intl, Domestic, etc) | Lead Engineer
Discovery, Planning, Design | Discovery | Paging | Paging - OHP | Lead Engineer
Discovery, Planning, Design | Discovery | Paging | Paging - Phone Paging | Lead Engineer
Discovery, Planning, Design | Discovery | Faxing | Faxing (ATA vs Cloud vs other) | Lead Engineer
Discovery, Planning, Design | Discovery | Analog | Call buttons, POTS lines, PLARs | Lead Engineer
Discovery, Planning, Design | Data Collection | Voice Config | User Template (DIDs and UPNs, Shared Lines, etc) | Lead Engineer
Discovery, Planning, Design | Data Collection | Voice Config | E911 Template | Lead Engineer
Discovery, Planning, Design | Data Collection | Voice Config | AA/CQ Template | Lead Engineer
Discovery, Planning, Design | Data Collection | Analog | ATA Zero Touch Config Template | Lead Engineer
Discovery, Planning, Design | Planning | Voice Config | Migration Waves & Port Events | SOW
Discovery, Planning, Design | Planning | Voice Config | Licensing Procurement | Customer
Discovery, Planning, Design | Planning | Voice Config | Handset Procurement | Customer
Discovery, Planning, Design | Planning | Analog | ATA Procurement | Customer
Discovery, Planning, Design | Planning | Direct Routing | SBC Procurement | Customer
Discovery, Planning, Design | Planning | Paging | Paging Adapter Procurement | Customer
Discovery, Planning, Design | Design | Paging | Paging - OHP | Lead Engineer
Discovery, Planning, Design | Design | Paging | Paging - Phone Paging | Lead Engineer
Discovery, Planning, Design | Design | Faxing | Faxing (ATA vs Cloud vs other) | Lead Engineer
Discovery, Planning, Design | Design | Analog | Call buttons, POTS lines, PLARs | Lead Engineer
Discovery, Planning, Design | Design | Voice Config | E911 Finalization | Lead Engineer
Discovery, Planning, Design | Design | Voice Config | AA/CQ Finalization | Lead Engineer
Discovery, Planning, Design | Design | Voice Config | Shared Lines Finalization | Lead Engineer
Discovery, Planning, Design | Design | Voice Config | User and Shared Device Finalization | Lead Engineer
Staging and Configuration | Staging | Licensing | User Licenses Procured | Customer
Staging and Configuration | Staging | Licensing | Shared Device Licenses Procured | Customer
Staging and Configuration | Staging | Licensing | Resource Account Licenses Procured | Customer
Staging and Configuration | Staging | Licensing | Teams Premium Licenses Procured | Customer
Staging and Configuration | Configuration | Voice Config | Shared Device Accounts Created | Lead Engineer
Staging and Configuration | Configuration | Voice Config | Resource Accounts Created | Lead Engineer
Staging and Configuration | Configuration | Voice Config | M365 Groups Created (CQ's, VM, etc) | Lead Engineer
Staging and Configuration | Staging | Analog | ATA Connected | Customer
Staging and Configuration | Staging | Operator Connect | iPilot Test Numbers provisioned | Lead Engineer
Staging and Configuration | Staging | DRaaS | iPilot Test Numbers provisioned | Lead Engineer
Staging and Configuration | Staging | Voice Config | Pilot group identified | Customer
Staging and Configuration | Staging | Direct Routing | SBC Connected | Customer
Staging and Configuration | Configuration | Voice Config | Pilot group configured with Teams Voice | Lead Engineer
Staging and Configuration | Configuration | Voice Config | E911 Configured | Lead Engineer
Staging and Configuration | Configuration | Voice Config | Auto attendants configured | Lead Engineer
Staging and Configuration | Configuration | Voice Config | Call queues configured | Lead Engineer
Staging and Configuration | Configuration | Voice Config | Dial Plans configured (if required) | Lead Engineer
Testing and Validation (Operational Readiness) | Testing | Standard | Test Plan Executed | Voice Eng
Testing and Validation (Operational Readiness) | Testing | Standard | Test Failures Remediated or identified and communicated | Voice Eng
Implementation | User Readiness | Standard | User Communication and Training has been delivered or scheduled | Customer

## Sheet1
["Initiation", "Project Onboarding", "Standard", "Engineer Review of SOW", "Lead Engineer"],
["Initiation", "Project Onboarding", "Standard", "Internal Kickoff Call", "PM"],
["Initiation", "Project Onboarding", "Standard", "Client Kickoff Call", "PM"],
["Initiation", "Customer Onboarding", "Operator Connect", "Enable NWN as Operator Connect provider", "Customer"],
["Initiation", "Customer Onboarding", "DRaaS", "NWN Integration through App Auth", "Customer"],
["Discovery, Planning, Design", "Discovery", "Standard", "Initial Discovery Meeting with Customer", "PM"],
["Discovery, Planning, Design", "Discovery", "Voice Config", "NWN Access", "Customer"],
["Discovery, Planning, Design", "Discovery", "Voice Config", "Phone Number Migration - High Level", "Lead Engineer"],
["Discovery, Planning, Design", "Discovery", "Voice Config", "Dialing Pattern Requirements", "Lead Engineer"],
["Discovery, Planning, Design", "Discovery", "Voice Config", "Routing Requirements (Intl, Domestic, etc)", "Lead Engineer"],
["Discovery, Planning, Design", "Discovery", "Paging", "Paging - OHP", "Lead Engineer"],
["Discovery, Planning, Design", "Discovery", "Paging", "Paging - Phone Paging", "Lead Engineer"],
["Discovery, Planning, Design", "Discovery", "Faxing", "Faxing (ATA vs Cloud vs other)", "Lead Engineer"],
["Discovery, Planning, Design", "Discovery", "Analog", "Call buttons, POTS lines, PLARs", "Lead Engineer"],
["Discovery, Planning, Design", "Data Collection", "Voice Config", "User Template (DIDs and UPNs, Shared Lines, etc)", "Lead Engineer"],
["Discovery, Planning, Design", "Data Collection", "Voice Config", "E911 Template", "Lead Engineer"],
["Discovery, Planning, Design", "Data Collection", "Voice Config", "AA/CQ Template", "Lead Engineer"],
["Discovery, Planning, Design", "Data Collection", "Analog", "ATA Zero Touch Config Template", "Lead Engineer"],
["Discovery, Planning, Design", "Planning", "Voice Config", "Migration Waves & Port Events", "SOW"],
["Discovery, Planning, Design", "Planning", "Voice Config", "Licensing Procurement", "Customer"],
["Discovery, Planning, Design", "Planning", "Voice Config", "Handset Procurement", "Customer"],
["Discovery, Planning, Design", "Planning", "Analog", "ATA Procurement", "Customer"],
["Discovery, Planning, Design", "Planning", "Direct Routing", "SBC Procurement", "Customer"],
["Discovery, Planning, Design", "Planning", "Paging", "Paging Adapter Procurement", "Customer"],
["Discovery, Planning, Design", "Design", "Paging", "Paging - OHP", "Lead Engineer"],
["Discovery, Planning, Design", "Design", "Paging", "Paging - Phone Paging", "Lead Engineer"],
["Discovery, Planning, Design", "Design", "Faxing", "Faxing (ATA vs Cloud vs other)", "Lead Engineer"],
["Discovery, Planning, Design", "Design", "Analog", "Call buttons, POTS lines, PLARs", "Lead Engineer"],
["Discovery, Planning, Design", "Design", "Voice Config", "E911 Finalization", "Lead Engineer"],
["Discovery, Planning, Design", "Design", "Voice Config", "AA/CQ Finalization", "Lead Engineer"],
["Discovery, Planning, Design", "Design", "Voice Config", "Shared Lines Finalization", "Lead Engineer"],
["Discovery, Planning, Design", "Design", "Voice Config", "User and Shared Device Finalization", "Lead Engineer"],
["Staging and Configuration", "Staging", "Licensing", "User Licenses Procured", "Customer"],
["Staging and Configuration", "Staging", "Licensing", "Shared Device Licenses Procured", "Customer"],
["Staging and Configuration", "Staging", "Licensing", "Resource Account Licenses Procured", "Customer"],
["Staging and Configuration", "Staging", "Licensing", "Teams Premium Licenses Procured", "Customer"],
["Staging and Configuration", "Configuration", "Voice Config", "Shared Device Accounts Created", "Lead Engineer"],
["Staging and Configuration", "Configuration", "Voice Config", "Resource Accounts Created", "Lead Engineer"],
["Staging and Configuration", "Configuration", "Voice Config", "M365 Groups Created (CQ's, VM, etc)", "Lead Engineer"],
["Staging and Configuration", "Staging", "Analog", "ATA Connected", "Customer"],
["Staging and Configuration", "Staging", "Operator Connect", "iPilot Test Numbers provisioned", "Lead Engineer"],
["Staging and Configuration", "Staging", "DRaaS", "iPilot Test Numbers provisioned", "Lead Engineer"],
["Staging and Configuration", "Staging", "Voice Config", "Pilot group identified", "Customer"],
["Staging and Configuration", "Staging", "Direct Routing", "SBC Connected", "Customer"],
["Staging and Configuration", "Configuration", "Voice Config", "Pilot group configured with Teams Voice", "Lead Engineer"],
["Staging and Configuration", "Configuration", "Voice Config", "E911 Configured", "Lead Engineer"],
["Staging and Configuration", "Configuration", "Voice Config", "Auto attendants configured", "Lead Engineer"],
["Staging and Configuration", "Configuration", "Voice Config", "Call queues configured", "Lead Engineer"],
["Staging and Configuration", "Configuration", "Voice Config", "Dial Plans configured (if required)", "Lead Engineer"],
["Testing and Validation (Operational Readiness)", "Testing", "Standard", "Test Plan Executed", "Voice Eng"],
["Testing and Validation (Operational Readiness)", "Testing", "Standard", "Test Failures Remediated or identified and communicated", "Voice Eng"],
["Implementation", "User Readiness", "Standard", "User Communication and Training has been delivered or scheduled", "Customer"],